2017 ILLINOIS HIGH SCHOOL THEATRE FESTIVAL

NOVEMBER 19-20, 2016 MEETING AGENDA

Krannert Center UIUC

SATURDAY MORNING, NOVEMBER 19, 2016

Choral Rehearsal Room

8:30 – Play Selection  (Tim & Michelle) meets with Nathaniel, Kurt, Allan, LaDonna & UIUC tech rep(s) to review and schedule

9:00 – Workshops meet to establish and proof the schedule.

SATURDAY AFTERNOON, NOVEMBER 19, 2016

Orchestra Rehearsal Room

12:30 – Remainder of the Committee Members arrive for planning meeting.  Lunch will be served.  We will have a working lunch to finish proofing the items on the list below.

1:00 – Full Committee Convenes

- Full Committee meets to assign responsibilities for the day.

- Approve minutes from the September meeting

- Report of Play Selection Evaluation Committee					           A.	Number of submissions

B.   Number of Full-Lengths

C.	Number of Showcases

D.	Number of Respondents

E.   Review slate of shows

F.   Justify selection (include geography and type of school, breakdown by region)

- Approval of Play Selection Slate of Shows – Before we adjourn, Workshops state number and types of workshops still needed. Call friends during the work session.

- Temporary Adjournment to Notify Directors of Selection Status

  - Other tasks to be completed at this time:

    - Auditions – audition schedule

    - Workshops – continue on schedule

    - Exhibit - layout

    - Proofing

    - LaDonna and Nathaniel– meet with monitors

- Full Committee reconvenes:

  - Review Audition Schedule

  - Finalize Proofing

  - Move to Sunday agenda items if time allows

- Adjourn for Dinner – Plan is to adjourn by 5:30 pm – Group reservation for dinner at Destihl in Champaign 7:00 pm

SUNDAY, NOVEMBER 20, 2016

Orchestra Rehearsal Room

9:00 – Full Committee reconvenes – we will have a working lunch at noon and take a group picture - 9:30 am

- Current Budget Report

- Review December e-mail							                        A.     Preliminary Registration Report (Review Festival schedule – accurate seat count       	for each hour (workshops and shows) 						1.	Number of attendees								2.	Number of schools								3.	Preliminary wait – list numbers

- Check schedule for space conflicts and personnel conflicts			           A. 	Workshops									           B.	Auditions – Performance times						             C.	Performances

- Committee Updates – What have you accomplished since September?	          A.	Executive Director–                                                                                     		1.	Thursday on-site responsibilities:				            				a.	Registration areas					            				b.	Fest Gear						            				c.	Welcomes for Opening Ceremonies								1.	Welcome from UIUC				           					2.	Administrator Award

3.	Friday night Sponsor Reception responsibilities:						a.	Address sponsors/exhibitors: 							b.	ITA President address									c.	Introduction of 2017 Director								d.	Introduction of 2018 Director					4.	Opening Performance – included in Festival program				5.	Sponsors Check-in – location and times						6.	Meals for Committee members during Festival					7.	Scholarships – Do we have any?					           B.	All-State											1.	Schedule at Festival									2.	Distribution of tickets to All-State families 						3.	College Auditions									4.	Ushers											5.	Copy deadlines for program - 							6.	Donations								           C.	Auditions											1.	How many are participating?	 - (Juniors/Seniors?)					2.	# of acting										3.	# of tech										4.	Monitor needs									5.	Scheduling										6.	Plans for notification for audition times 						7.	Plans for notification of “callbacks”							8.	Power for college reps								9.	Lunches for college reps (acting)							10.	Breakfast for college reps? (tech and acting)				           D.	Exhibits											1.	Number of exhibits                                               					2.	# of colleges										3.	# of vendors										4.	Layout                              						      		5.	Needs from other committees							6.	Notification to exhibitors								7.	Check-in at 12:00, set-up at 8:00 am – change in schedule				8.	Feedback from exhibitors						           E.	Technology											1.	App set up & application								2.	Slide Show of Schools	                                                              				3.	Promotions									3.	On-line programs. Are we including ads?					 F.	Hospitality/Mentors										1.	Staffing in lounge? 									2.	New sponsor update									3.	Refreshments								              G.	Play Selections										1.	Tech meeting December 11th at 10:00 am, meet in Krannert Center lobby		2.	Materials from each school for slide show						3.	Add-on numbers                                                                				4.	Ushers needed									5.	Plaques										6.	House Managers									7.	Feedback from directors and house managers					8.	Any warning labels for shows?							9.	Please remind all that we will hold ALL curtains (except All-State)

5 minutes for rush seating without tickets

H.	Promotions

1.	Item proofs for each being sold						             2.	Order totals

3.	Needs at Festival (photos for slide show? Mannequins,

cash registers, shelving)

4.	Staffing needs										5.	Deposits of money									6.	Cash registers & credit card terminals						7.	Monitor t-shirts/tech shirts								8.	Wristbands for the dance						             I.	Workshops											1.	Number of presenters									2.	Categories and symbols								3.	Space issues?										4.	Needs at Festival									5.	Signage – Large enough to be seen							6.	Last minute changes sheet for packet – Do we still do this?				7.	Monitor meeting									8.	Exit surveys								            J.	Friday Night Activities										1.	Dance											2.	Plans for activities									3.	Sponsors reception – notify prior that no alcohol			           K.	Local Arrangements										1.	Update on Festival spaces								2.	School registration numbers								3.	Special needs? (interpreters, wheelchairs, etc.)					4.	Lanyards, boxes, other materials/supplies			                         L.	Student Representatives/Monitors 							                  	1.	Building Supervisors					                    			2.	Numbers for each locations 								3.	Where will the lunch pick-up be located						4.	Do you still need monitors?					             	          M.	Graduate Credits/CPDUs						                        N.	Development										             	1.	Corporate Sponsorship								2.	Additional needs									3.	Advertisement #s									4.	Advertisement placement in the booklet			           	           O.	Historian/Documentarian							           P.	ITA Liaison

- Review/Update list of Packet Contents

A.	Sponsor Packet:

    - Badges – color-coded for students and sponsors

    - Festival program

    - Tickets to performances

    - Festival Update

    - Festival Survey (online through LaDonna)

    - Certificates?

    - Restaurant list

    - Visitor Guide

    - Campus Map/Parking

    - Lunch tickets

  - Workshop Leader Packet:

    - Welcome Letter

    - Badge(s)

    - Festival program

    - Festival Update

    - Certificates?

    - Restaurant list

    - Visitor guide

    - Campus map/parking

  - Exhibitor Packet:

    - Welcome Letter

    - Badge(s)

    - Festival program

    - Festival Update

    - Certificates?

    - Restaurant list

    - Visitor guide

    - Campus map/parking

- Wait List Update

- Festival Feedback

- Next Festival Director’s, Nathaniel Haywood, announcement of Theme and All-State Show/Director

- Meeting Place and Time for pre-Festival meeting on Wednesday, January 4, 2017 – 8 pm in the Studio Theatre

- Post-Festival Meeting – will meet after the All-State performance for a brief meeting.

- Change-over meeting – begin preparing reports in December because of short turn-around time.  Meeting is January 22nd in the Orchestra Rehearsal Room.

- ITA Representative

- Items to finish the week after the November meeting:

- By 11/27: Put together all pieces of the Festival program to send to designer (Michelle)

- By 11/25: Send out workshop leaders letter (Michelle)

- Send out Principal congrats letter (Tim & Michelle)

- Send out Exhibitor letter  (Vic and Gary)

- Move schools/exhibitors off waiting list (Michelle)

- Order lanyards, name badge holders, ribbons, etc. (Michelle)

- Get parking info (Michelle)

- Review to-do list for December and January

December

- By 12/2: Collect med forms and payments for add-ons (Michelle)

- 12/4: College Auditions schedule posted (Adam, Jessica & Michelle)

- By 12/5: Enter add-on registrations (Michelle)

- 12/2-7: Full Committee reviews 1st draft of Festival program (Michelle)

- 12/6: Pre-registered workshop requests due – if any (Liesl & Anna)

- 12/7: Revisions of 1st draft of Festival program due to designer (Michelle)

- 12/9: Digital Slideshow submissions due (Thom and Dennis)

- 12/9-12: Sub-committee reviews 2nd draft of Festival program (Michelle, Aimee-Lynn, Kurt, LaDonna, Nathaniel) & ITA 2nd VP (Carm) must see 2nd and subsequent program drafts

- 12/11: Attend tech meeting for selected productions

- 12/11: Get engraving info for all Full-Length/Showcases/All-State plaques – all productions get them (Tim & Michelle B to Michelle M)

- 12/12: Order production plaques (Michelle)

- 12/12: Revisions of 2nd draft of Festival program due to designer (Michelle)

- Post the following items on the website: (Michelle & Aimee-Lynn)

  - Review Participation Guidelines on website

  - News Release?

  - Plan Your Festival Schedule

  - Parking info/maps

  - Festival Program – 12/16 or 12/18

- Assign pre-registered workshops and notify schools (tickets needed???)

- Confirm UIUC student security plan, EMT (medical), interpreters (if needed)  and other personnel for Festival (Michelle)

- 12/14: December mailing (email) sent to schools (Michelle and LaDonna)

- 12/14: Designer sends 3rd proof of Festival Program (Michelle)

- 12/14-15: Sub-committee reviews 3rd/final proof (Michelle, Aimee-Lynn, Kurt, Nathaniel, Carm, & LaDonna)

- 12/16: Email notification to schools re: All-State & Opening Performance   assignments (Allan)

- 12/16: Revisions of 3rd/Final of Festival program due to designer

- 12/16: Final Approval of Program (LaDonna and Michelle)

- 12/16 or 18 (at latest): Festival Program to printer (Michelle)

- Start keeping track of changes to be included on program addendum sheet

- Print certificates if any (who will handle this?)

- Print name badges (exhibitors, workshop leaders, sponsors, Committee)

- Stuff lunch ticket envelopes

- Prepare arrival packets

- Prepare 8.5x11” signs for rooms for each Workshop (check with UIUC about procurement.  Monitors put them up.) – Who makes them?

- Lobby Signs

- Program cash registers?

Between Christmas Eve and New Year’s

- 1/3-5: UIUC staff stuff programs into school packets

January 3rd (Tuesday)

- 1/3: All-State Staff & Tech arrive at UIUC

January 4th  (Wednesday)

- Registration materials moved to KCPA

- Festival Planning Committee meeting at 8 pm at Krannert Studio Theatre

  - Give committee their packets

  - Review Festival Program for corrections/changes for Festival update page

  - Review of tasks to complete Thursday from 9 am – 4 pm

January 5th (Thursday)

- Post update info on special media and lobby slide show

- Full-Length/Showcase ticket stuffing (KCPA Studio Theatre, 9 am-Noon)

- Set up exhibit area

- Set up FESTGEAR

- Registration begins at 4 pm

January 5th-7th (Thurs-Sat)

- FESTIVAL!!!!

January 7th  (Saturday)

- Post-Festival Committee Meeting following final All-State performance – KCPA Studio Theatre, approx. 5:30 pm

- Post-Festival Committee Dinner for those who wish to join – Big Grove Tavern, approx. 7pm

- Other Items

- Finalize Proofing of Festival Program as needed

- Adjourn (estimate – 4:00 pm, but could be earlier depending on how far we get on Saturday)